## Sheet1
| Week 1 6/29 - 7/5 | Week 2 7/6 - 7/12 | Week 3 7/13 - 7/19 | Week 4 7/20 - 7/26 | Week 5 7/27 - 8/2 | Week 6 8/3 - 8/9
Create goal/recipe doc | Phoenix
Create & send out GANTT | Kristi
Census data CSV variable search | Griffin & Wyatt
Variables finalized, add to recipe doc |  | Kristi
Create basical global variables, test outputting |  | Phoenix
User input & print functions |  |  | Griffin
Convert data for user export |  |  |  |  | Courtney
Start ReadMe user guide file for user |  |  | Kristi
Spot check code for errors |  |  |  | Wyatt
Finalize recipe & goal doc |  |  |  |  | Kristi
Make sure goal doc matches ReadMe and program code | [5 empty] | All
Final check of code for errors & issues | [5 empty] | All